## Document Information
Document Information | Ref | Link
| 1 | Monitoring planner - PRAGMO
| 2 | Home - CastCo
Title: Collaborative Monitoring Planner Template
Authors: Paul Hulme (Rivers Trust), Simon Browning (Rivers Trust)
Version & date: V3.2 August 2025
Acknowledgments:
We would like to thank the River Restoration Centre whose PRAGMO planning spreadsheet (Link 1), which was used and adapted by the Castco Demonstration Catchments over the course of the project leading to this monitoring template.
We are indebted to the volunteers, volunteer coordinators and many people from partner organisations involved in the CastCo project, who invested much time and effort during the project to produce useful collaborative monitoring plans for their Demonstration Catchments.
Link to hosting website: Link (2)
Table of Contents
- Document Information
- Introduction
- Template Planner
- Planner with Example Entries

## Introduction
Introduction to Planning Your Monitoring | Ref | Link
| 1.1 | Classifications data for Teme Management Catchment ¦ Catchment Data Explorer
| 1.2 | Leigh-Cradley Bk - conf Suckley Bk to Teme ¦ Catchment Data Explorer ¦ Catchment Data Explorer
| 1.3 | Data Explorer ¦ CaSTCo Data Hub
| 1.4 | Placeholder for link to CastCo Data Hub User Guide
| 1.5 | SE_RBD_WB_Status_Pivot_2023
| 1.6 | RNAGS_2023
| 1.7 | Sewage Map ¦ The Rivers Trust
| 2.1 | Guidance: defining your primary monitoring purpose - CastCo
| 2.2 | Making a difference - CastCo
| 2.3 | CastCo - Collaborative monitoring planning
Note on A15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As discussed, I think this needs a little more specific guidance, perhaps by directing people to a small number of data sources with some hand holding regarding how to use them
Data take valuable time and effort to gather so, before you start monitoring, it is important to think about what your group wants to know, how you can use your data to create change and what resources you have.
1. Background information
It is important to understand the key features and background information in your river catchment (this usually develops over several months). Useful data sources are:
1) What does the Environment Agency say about the health of your river?
a) EA Catchment Data Explorer - See example links (1.1) and (1.2)
i) WFD Water Body Classification
ii) Reasons for Not Achieving Good Status (RNAGS)
b) CastCo Data Hub and User Guide - See links (1.3) and (1.4)
i) Water Framework Directive (WFD) Catchment Classification
ii) WFD Site Classifications
iii) WFD Water Body Status for your River Basin District, e.g. Anglian River Basin District - See link (1.5)
iv) RNAGS - See link (1.6)
2) Where is the EA monitoring?
a) CastCo Data Hub - See links (1.3) and (1.4)
i) Monitoring Sites and Incidents folder
ii) Environment Agency Water Quality Sampling Data folder
3) Where are other citizen science groups monitoring?
a) CastCo Data Hub - See links (1.3) and (1.4)
i) National Citizen Science Data folder
ii) Local Citizen Science Data folder
4) Where are the sewage treatment works & spills?
a) Rivers Trust Sewage Spill map - See link (1.7)
b) CastCo Data Hub - See links (1.3) and (1.4)
i) Consented Discharges - Sewage
ii) Event Duration Monitoring
5) What is the land cover?
a) CastCo Data Hub - See links (1.3) and (1.4)
i) Land Cover Map (2023)
2. Starting Questions
Once you have looked at some of the background information, ask:
1) What gaps are there in your current knowledge?
2) What issues or problems are you seeing on the ground?
3) What is your purpose in monitoring? - See link (2.1)
4) What are your objectives for the river?
5) What questions do you want your monitoring to answer?
6) How are you planning to use the data you collect?
7) What changes or impact would you like to see as a result of your monitoring? - See link (2.2)
You can find more information in the Knowledge base on the CastCo website - See link (2.3)
3. How to use this template?
This template is designed to be used to in conjunction with the guidance on Collaborative Monitoring Planning on the CastCo website (Link 2.1). It is based on versions used by the 8 Demonstration Catchments during the CastCo project.
Once you have looked at the relevant "Background Data" and considered the "Starting Questions" above, get together with any partners you are working with and start filling out the blank template with your monitoring activities - one line for each activity. Do not worry about filling in every cell - just use it as a checklist to get going.
The "Planner with Example Entries" tab includes entries from some of the Collaborative Monitoring Plans produced by the CastCo Demonstration Catchments. These lines are only illustrative examples. They were taken from several different plans so your plan may have far fewer lines - and that's ok.
Examples of actual Collaborative Monitoring Plans produced by the CastCo Demonstration Catchments are given on the CastCo website, here: Kat, placeholder for link when it is ready

## Template Planner
River XX Collaborative Monitoring Planner |  |  |  | Last Updated: | DD-MMM-YYYY
Why |  |  |  | What, Where, When etc. | [5 empty] | Management
Purpose | Monitoring Question | Background Data | Data Use | What | How | Where | QA | When | Who | Priority | Data Management | Feasibility | Comments
What is the primary purpose of this monitoring activity? 1) Engagement 2) Surveillance 3) Investigation 4) Evaluation (See Intro tab, Starting Questions) | Write the aim of the monitoring in the form of a question. (See Example entries tab) | 1) What background / baseline data do you have access to that is related to your monitoring question? 2) What gaps are there? 3) Who else is working in your area and what data might they hold? | 1) How will you analyse & use the data you collect? 2) How will this relate to the impact you want to see? (See Intro tab, Starting Questions) | What are you going to measure? | What methods are you going to use? | Where are the most important places to survey and where do you have access? | What QA procedures will you use to produce data of adequate quality for your purpose? | What periods over the year and how often? | Who is going to do this? (Names of people or groups) | Will you aim to do this in Year 1 or beyond? | How will you store & share your monitoirng results? | 1) Do we have volunteer capacity (if not, or how do we plan to grow this)? 2) Do we have the money? 3) Are there any key obstacles?
--- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | ---
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reference: Guidance: defining your primary monitoring purpose - CastCo
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reference: Making a difference - CastCo

## Planner with Example Entries
River XX Collaborative Monitoring Planner |  |  |  | Last Updated: | DD-MMM-YYYY
Why |  |  |  | What, Where, When etc. | [5 empty] | Management
Purpose | Monitoring Question | Background Data | Data Use | What | How | Where | QA | When | Who | Priority | Data Management | Feasibility | Comments
What is the primary purpose of this monitoring activity? 1) Engagement 2) Surveillance 3) Investigation 4) Evaluation (See Intro tab, Starting Questions) | Write the aim of the monitoring in the form of a question. | 1) What background / baseline data do you have access to that is related to your monitoring question? 2) What gaps are there? 3) Who else is working in your area and what data might they hold? | 1) How will you analyse & use the data you collect? 2) How will this relate to the impact you want to see? (See Intro tab, Starting Questions) | What are you going to measure? | What methods are you going to use? | Where are the most important places to survey and where do you have access? | What QA procedures will you use to produce data of adequate quality for your purpose? | What periods over the year and how often? | Who is going to do this? (Names of people or groups) | Will you aim to do this in Year 1 or beyond? | How will you store, analyse & share your monitoirng results? | 1) Do we have volunteer capacity (if not, or how do we plan to grow this)? 2) Do we have the money? 3) Are there any key obstacles?
Surveillance | Where are the gaps in our knowledge and exisiting monitoring? | 1) EA Catchment Data Explorer 2) CastCo Data Hub 3) Angling Trust data | To target future volunteer monitoring. |  | Gather data on where the EA and other citizen science groups (e.g. RiverFly, Angling Trust WQMN, Earthwatch) are sampling in our area.
Surveillance | What is the health of River XX? | 1) EA Catchment Data Explorer 2) CastCo Data Hub 3) EA WIMS data (phosphate, DO, nitrates, sediment). 4) RiverFly | To create a citizen science monitoring programme to investigate water quality and river health & sharing the results via catchment scorecards to support and inform decision-making. | Phosphate, nitrate, turbidity, total dissolved solids (TDS), temperature. | Hanna meters for phosphate (HI-713), Kyoritsu PACKTEST test capsules for nitrate, Secchi tube for turbidity, HM Digital EC-3 for TDS. Also Mudspotter | Picking up on mothballed EA sampling sites | WQ Test Kit: Pre-checked/evaluated methodology. User and calibration training with volunteers & trial period. Compare with lab-based data annually. | Ideally fortnightly - at least monthly |  |  | Anlaysis & sharing via water body scorecards |  | Potential to combine with Riverfly data, once RiverFly monitoring builds momentum locally.
Surveillance | Where are the problem reaches where pollution is impacting water quality and the invertebrate population? |  | To identify the problem reaches & target remedial action | Phosphate, Inverts | Hanna low range phosphate checker (HI-713) RiverFly | Upstream and downstream of wastewater treatment works | [5 empty] | Aspiration is to build both invertebrate sampling and analysis capability. No resource to fully analyse invertebrate results at present | Long-term goal. New volunteers with relevant experience needed to progress this.
Investigation | What are the key drivers of fish kills observed in River XX in recent years? |  | To identify the factors contributing to fish kills | Ammonia, Phosphate, Dissolved oxygen | Medium range Hanna checker for ammonia (HI-715). Can we try Continuous monitoring and or sampling for Dissolved Oxygen? | Upstream of fish kills & focussing on locations XX & YY | [5 empty] | Only one overstretched volunteer has done DO monitoring before. Capacity needs to be expanded to make this viable. | Fish kills tend to occur following rain at the end of long periods of dry weather. Likely linked to poor quality water from previously dry, stagnant drains. Interesting to look at where poor quality water is coming from. Role for Mudspotter?
Investigation | What methods of bacteria monitoring are available and suitable for citizen science. |  | To steer the direction of future bacteria sampling across the catchment. | Bacteria or their proxies using different trial methods & compare with lab analysis samples to determine accuracy. | A series of waterblitzes to trial: AquagenX, IDEXX Colilert, IDEXX Tecta B16, Fluidion Alert 1, R-cards | On as many water bodies in our catchments as possible |  | Arrange waterblitzes for 2 years roughly every 3 months (so each season).
Investigation | What monitoring methods can farmers use to monitor their soil health, create better soils and improve WQ on their farms? |  | To see whether simple soil monitoring methods are practice and useful to farmer citizen scientists | Various soil properties: water infiltration, soil biology, soil texture | 1) Water infiltration, Visual evalutaion of soil structure, Earthworm count, Soil texture. 2) Compare with lab testing. | In the area of the XX farmers cluster group | Training of volunteers, standardised equiptment, reliable equiptment, expert-led data audit, lab-based data. | Monthly |  |  |  |  | We want to engage and empower the farming community and local communities to monitor soil health through citizen science monitoring methods and report on soil health.
Surveillance | What & where are the sources of poor water quality affecting the headwaters of the River XX? |  | 1) To identify problem reaches/point sources & diffuse pollution to help target remedial measures, 2) To inform next steps of the XX CaBA partnership, | Phosphate, ammonia, nitrate, suspended solids | Hanna meters for phosphate (Low range phosphate checker HI-713) & ammonia, Kyoritsu PACKTEST test capsules for nitrate, Secchi tube for turbidity, Mudspotter | Headwaters XX, YY & ZZ |  | Every 2 weeks
Investigation | Currently the XX waterbody is assessed by the EA as 'Certain no eutrophication problem'. Does Citizen Science data support or oppose this assessment? |  | To add weight to the EA eutrophication assesment using CS data. | Phosphate, nitrate, sediment, algae | Hanna meter for phosphate , Kyoritsu test strips for nitrate, Secchi tube for turbidity, Mudspotter, RAPPER for algae
Investigation | Where are there river connectivity problems due to barriers (affecting water voles & brown trout)? |  | To identify locations where bypass or removal of barriers can improve the river ecology |  | River survey and map desk-based survey.
Investigation | Where are the major sources of sediment (roads, farms, bank erosion) entering the river? Do other data sources already collected highlight this? | 1) The EA 1m LIDAR potential overland flow pathways 2) SciMap 3) EA WIMS (sediment) | To target sediment interventions such as cover crops, SuDS, sediment traps, integrated wetlands where most these will produce benefits. | Silt pathways into the river | Mudspotter
--- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | ---