## Arun Demo+
Reference | Purpose | Why | Use | What | Priority | How | Where | QA | Data | When | Who | Cost | Confidence | When to stop | Evaluation | Visualisation | Location | Storage | Location | Archive data? | Format | Where? | How long? | Reflection | WSRT Reflection | SWS Reflections | Status | CaSTCo Deliverables | Future Aspirations
Question Number | Primary purpose of monitoring: Engagement, Surveillance, Investigation, Evaluation | Write the objective of the monitoring in the form of a question | How will you use the data you collect? | What is your monitoring objective/what are you trying to observe? (Your monitoring hypothesis) | Year 1 or beyond | What methods are you going to use? | Location | What QA procedures will you use? | Add information on the baseline data you have collected (type, frequency, method used) | What periods over the year and how often? (to indicate variability) | Who is going to do this? | (Can be in kind) | High/ medium/ low confidence that the monitoring will answer the question in column B | When to stop monitoring? Date (inc macro to highlight data which should no longer be collected) | Who will collate and evaluate the monitoring results (also when and how)? | How will you present and share the monitoring results? | Name of water body | How will you store the data | Name of water body | Archive data? Yes/No | Spreadsheet/WIMS/report/other | Where archived? FWW/FBA/WIMS/local | event / date / ongoing | Have we achieved this? Is this question still relevant? Why/Why not? How do we evidence this? What does success look like? | Feb 2025 Comments and CMP Updates | August 2025 Comments and CMP Updates
1 | Investigation | Can we identify gaps in water quality monitoring data in the Arun Demo area? Assessment should consider both spatial and temporal gaps. | To inform next steps of Arun Demo CaSTCo project. To support understanding of river health in the Arun and Western Rother. | To identify all existing monitoring being undertaken. Are there any gaps that need to be filled? Identify opportunities. | ASAP - One of first things completed | Desk study - data and information gathering exercise. | Arun demo area | Engagement with organisations monitoring WQ to ensure any limitations and interpretation of results are understood. | EA, SWS. Any other groups such as Angling Trust, Peterfield Volunteer Group, Eco Rother etc. | Complete & Ongoing annually | WSRT, supported by demo partners (data and information sharing). | Low | High | When we are confident that all monitoring significant spatial and temporal gaps have been noted. | WSRT & collaboratively reviewed by demo partners | High level targeting summaries | Arun demo area | CaBA Data Explorer (existing data) Demo sharepoint area | Arun and Western Rother Catchment | No- existing data review | Report | n/a | End of Jan 2024 | Yes, achieved, yes still relevant for both WQ & Soil ACTION on Keir to produce high level targeting strategy for CS WQ monitoring. Add opportunties to link to future data sets. | Main gaps identified and River Guardians/volunteers deployed. Continuous assessment of spatial/temporal monitoring from EA/SW/WSRT needed at least annually to successfully target WQ/River Health monitoring in the future. |  | Completed | Deliverable - mapped output showing pre and post project monitoring. Supported by CaSTCo Method audits. | Legacy - Annual review of monitoring locations and gaps. Collaboration between all monitoring entities (WSRT, SW, EA, Angling Trust, Chi Harbour, Friends of Groups etc) to pool data and utilising data for action. Utilise citizen science to enable wide spread catchment monitoring, filling regulatory gaps and provide wide scale, longterm baseline.
2 | Investigation | What citizen science methods are most representative to determine the status soil health? | To give information to farmers about how to understand and improve their soil health. Assess the citizen science methods. | To engage and empower the farming community and local communities to monitor soil health through citizen science monitoring methods and report on soil health. | This will be started in Year 2 | Soil health in terms of infiltration, macronutrients, micronutrients ect. To be confirmed co-designed process with farmers and other relevant citizen scientists. Baseline soil testing with lab-based analysis P, K, Mg, pH, Orgnaic Matter, Solvita, Bulk Density, Carbon levels & Textual Classification. Physicial assessments for Earthworms and VESS | Arun demo area | Training of volunteers, standardised equiptment, reliable equiptment, expert-led data audit, lab-based data | Literature and soil method audit review. Lab-based soil sampling to be collected as part of Soil SmARt project. | approx 2 times a year | farmers/landowners | £100K (not including volunteer hours) | High | Continuous until project end (with ambitious to continue project after CaSTCo) | WSRT are evaluating CS methods in terms of useability and accuracy, with S. Woodley Crop Services comparing to standard monitoring, and Cranfield University comparing research grade monitoring. Peridocially during the project via reporting. | Project reports, Soil mentor dashboard, excel spreadsheets | Arun demo area | Storage of CS data on Soil Mentor | Arun and Western Rother Catchment | To be agreed with citizen scientists as part of data agreement | TBD | TBD | Late 2023 - project end | Ongoing Soil SmARt Project to meet this monitoring objective. Project targeting based on engagement opportunities/gaps Yes, achieved, yes still relevant soil project. ACTION for Beth to do workshop summary of Engagement and collaboarative design workshop (14/09/23) & Kirsten to review. |  | Soilmentor subscription extension is clear validation of engagement and interest in a platform to record monitoring. Initial workshop and return invitation to Brinsbury College for soil health monitoring training is evidence of demand of the Face to Face, in field instruction. Cranfield comparisons selected, soil respiration, infiltration, PES data will help validate confidence in CS results. Geospatial insights help inform opportunity mapping. Evidence emerging that the CS approaches can be used with confidence when used to observe changes or trends. It is important to standardise the approach for consistency. The more CS observations made, the more motivation there appears to be to adopt practise change for improvement. The simple act of digging up and observing soil conditions, an activity prompted by the tool kit and tests is a valuable “observational approach” that can influence the need to address issues observed! | In Progress | 1. Soil SmART Toolkit & Instruction Sheets 2. Soil Method Audit Report 3. Comparative Analysis - Tiers of Soil Data 4. How to do video - Soil Citizen Science Monitoring | Soil Guardians - community-led citizen science soil monitoring Other interest groups - taking the learnings and trialling Soil SmARt approach Brinsbury Agricultural College Annual Training Day - soil monitoring training day for agricultural students.
3 | Investigation | Can species assemblages of aquatic invertebrates be indicators of the link between link water quality and soil health? | Data uploaded to Riverfly explorer platform. Analysis against turbidity, water temp, and dissolved oxygen. | Determine to status of riverflies in the Arun and Western Rother. Testing whether species diversity of aquatic inverts can be a biological link between water quality and soil health. | This will be started in Year 1 | Riverfly surveys (CS), visual obs of river and marginal habs, additional tests, such as DO and temp, which can also impact in aquatic inverts species counts and diversity | River Rother and Arun Catchments | Riverfly co-ordinator data audit | Historic riverfly and water quality monitoring data | Monthly - in ideal Riverfly monitoring months | ARRT and SDNPA Riverfly trained volunteers | Low | Med | Continuous to identify any trigger level breach | Riverfly Coordinator and ARRT |  | Arun demo area | Cartographer, Riverfly Database | Arun and Western Rother Catchment | Riverfly Monitoring Data | TBD | TBD | Ongoing | No, not relevant to revised scope of monitoring, to include in questions 1 & 3 and opportunity to add at latter stages of the project. In the demo area, the scheme has sadly lost momentum. | Further Riverfly training planned to increase data on the Rother. Summer 2025 |  | Completed | 1. Training Day - Riverfly training 2. Data uploaded on Riverfly Data Explorer | WSRT Riverfly data aspiration to be embedded into River Health Scorecards. More resource/training require to have catchment wide Riverfly Monitoring.
4 | Surveillance | How can we improve the spatial and temporal coverage of water quality monitoring using citizen scientists? | Continued assessment of river health. Informing future monitoring and remedial measures on problem reaches/hotspots. Inform and educate catchment stakeholders and communities on status of river health. | Create a citizen science monitoring programme to investigate water quality and river health, embedding the data into a data hub to support and inform decision making within the catchments. | Complete | Citizen Science monitoring following guidelines by PRAGMO/CaBA/Westcountry CSI. Field assessments of PO4, nitrates and turbidity, TDS, Temp. Visual assessment survey e.g. ecosystems; pollution; river characteristics; wildlife. Potential to include combine with Riverfly, once the scheme builds momentum again locally. | Arun demo area | WQ Test Kit QA - Pre-checked/evaluated methodology. User and calibration training with volunteers & trial period. Lab-based data (from SWS survillance monitoring). | WIMS (Phosphate, Nitrates, Turbidity, Dissolved O2), EA Catchment Explorer, Riverfly. | Monthly reccomended | Citizen Scientists & ARRT | £12K (not including volunteer hours or event costs) | High | Continuous. Fill gaps and identify hotspots. | ARRT and CS volunteers | Cartographer hosted on ARRT website | Arun demo area | Cartographer | Arun and Western Rother Catchment | TBD | Other, Cartographer | TBD | Ongoing | Ongoing, WQ monitoring programme launched. Success metric TBC e.g. before and after picture of active monitoring locations in the catchment. | Continuously ongoing. 1000 CS River Health surveys in 2024. 1600+ total Continuously increasing spatial coverage of CS WQ Monitoring across the catchment. Utilising CS River Guardians Site Heatmap/WoE Eutrophication layer to identify areas not covered by CS/areas of interest needing targeting/further recruitment Demonstrate impact (stats/hours/surveys/vols etc). Bringing this info to CaBA CP (AWSCP) for further input and discussion. |  | Completed | 1. River Guardians Programme and Cartographer 2. How to do videos 3. River Health Score Cards 4. River Guardian Volunteers video | Continue and expansion of the WSRT River Guardians Programme. Integration with SWS via Source-Pathway-Receptor Project / via Integrated Catchment Strategy Integration with EA inputting into annual Monitoring Strategy/Schedule for Solent South Downs.
5 | Investigation | Using a demo subcatchment, can we map, control, and monitor the impacts of I. glandulifera management? | To inform future INNS managment projects. | To quantify the benefits of I. glandulifera control - biodiversity, water quality (turbidity) etc. | Year 2 or beyond (low priority) | Citizen Science monitoring following guidelines by PRAGMO/CaBA/Westcountry CSI. Field assessments of PO4, nitrates and turbidity, TDS, Temp. Visual assessment survey e.g. INNS presence/absence; ecosystems; pollution; river characteristics; wildlife. | River Lod(?) | WQ Test Kit QA - Pre-checked/evaluated methodology. User and calibration training with volunteers & trial period. Lab-based data (from SWS survillance monitoring). | ARRT walkover survey reports, SDNPA data, SxBRC records. | Year round - monitoring. Summer - INNS control. | SWS, ARRT, SDNP Citizen Scientists, academic institution | Med | Med | Continuous | SWS, SDNP, ARRT | Cartographer, GIS, and report | River Lod, Western Rother (TBC) | Cartographer | River Lod, Western Rother (TBC) | TBD | Other, Cartographer | TBD | TBD | Potential project in the pipeline (TBC) ACTION Jen & Keir to discuss with Angela from South Downs National Park | Rother Coordinator Chloe Clarke pursuing with Angela W (SDNP) Still active in CMP? | HB bashing volunteer days undertaken. | Ongoing |  | SDNP led eradication strategy for Himalayan balsam.
6 | Project appraisal | Have we successfully collaborated with and empowered citizen scientists? | An assessment of collaboration & learnings to inform future projects and ways of working. | To measure our success of collaboration and empowerment of citizen scientists. | This will be started in year 1 | Feedback questionnaires, interviews, verbal feedback during events | Arun demo area | Social scientist-led questionnaires, interviews and any other feedback methods | Comparsion of Arun demo activities against recommendations for collaboration in catchment citizen science projects in the Rapid Evidence Assessment (REA) (CCRI, 2023). | At key milestones | CCRI | £80K | High | When the project has finished | CCRI | Co-created metric, end of project report | Arun and Western Rother Catchment | Demo area on CaSTCo sharepoint & included in end of project reporting | Arun and Western Rother Catchment | Yes, for 2 years after the end of the project. | Report | Local (UoG database) | Until project-end | Still relevant, CCRI package of works in progress. | Ongoing, CCRI leading this. Helping to facilitate interviews and feedback from CaSTCo Cit Scientists. See project appraisals below. |  | In Progress | 1. Citizen Science co-design guidance 2. Social Science Final Report 3. Rapid Evidence Assessment (Draft versions submitted) 4. Presentations | Academic papers (x2) Interviews with Project Teams and Citizen Scientists Dissemination and sharing learning with other citizen science groups in other catchments Promoting CaSTCo Network Wider Dissemination at relevant events and conference
7 | Investigation | Can we use a natural capital model, which focuses on water resources, to identify what areas/habitats could be 'protected' and 'restored' in the Arun demo area? | An engagement tool that will build a shared understanding of the demo area, identify shared priorities and opportunities. | To develop a natural capital model that can be used as a tool to engage, build a shared understanding of the Arun demo area, and identify stakeholder priorities. | This will be started in year 1 | Citizen Science survey data and ground truthing catchment walkovers. Catchment Stakeholder workshop(s). | Arun demo area | Higher tier monitoring and periodic data review (sensecheck). Catchment expertise and groundtruthing walkovers. | Opensource catchment data, data weighting exercise with catchment stakeholders | Workshop by March 2024 | South East Rivers Trust, SWS & ARRT | £20K | High | Continuous use to support targeting of measures | SERT and SWS | Natural Capital Maps & Report | Arun and Western Rother Catchment | TBC | Arun and Western Rother Catchment | No | Report & other | n/a | Ongoing | Yes, still relevant SERT Natural Capital Mapping work package covers this e.g. weighed maps. Opportunity for desk-based review of soil health & WQ data & other relevant datasets. |  | Re-scoped to remove Benefit Assessment agreed with Catchment Stakeholders. Focus on opportunity and how we can priortise delivery. | Completed | 1. NbS mapped outputs and methodology | Targeting post project monitoring with citizen science monitoring Where the opportunities are unclear - areas for monitoring to be undertaken to verify opportunities for NbS delivery
8 | Investigation | Can we develop the natural capital model to create a functional and effective nature-based solutions (NbS) opportunity map and high-level natural capital benefits assessment? | A demonstration of potential NbS opportunities for catchment resilience that deliver multiple natural capital benefits. An engagement tool. | To develop a functional and effective NbS opportunity tool (GIS map and high-level natural capital benefits assessment) to support the prioritization and identification of suitable NbS for catchment resilience. To embed this in SWS ways of working - measures indentification and how we work with catchment partners (and other stakeholders) in AWS catchments through the Integrated Cathment Strategy. | This will be started in year 2 | Citizen science survey data and ground truthing catchment walkovers. Catchment Stakeholder workshop(s). | Up to 5 strategic sub-catchments: Upper & Lower Lod Stanbridge Stream Upper Western Catchment Lower Eastern Catchment Upper Arun (TBC) | Higher tier monitoring and periodic data review (sensecheck). Catchment specialist expertise | Opensource catchment data, survey/monitoring data shared by catchment stakeholders. | TBA | SERT, SWS and ARRT | TBC | High | Continuous use to support targeting of measures | SERT and SWS | NbS Opportunity Maps & Report | Arun and Western Rother Catchment | TBC | Arun and Western Rother Catchment | No | Report & other | n/a | Ongoing | New question. Opportunity to take learning and info from other activities and embed this into the proposed opportunities. We will come back to this question soon, to make sure the wording and objectives remain relevant to this activity as it evolves. |  | As above | Completed | 1. Report & priorisation matrix | As above.
9 | Surveillance | Objective of monitoring is part of SWS internal Catchment Risk Assessment process for Surface Water Catchments and informs targeting (e.g. hotspots mapping) | To observe potential hotspots on sub-catchment level to support risk identification to raw water abstraction. | What are the catchment risks, are there potential hotspots on sub-catchment level? Are these exceptional breaches which could impact raw water abstraction? Surviellance and exceptional breaches which need proactive review and action. Monitoring for 191 WQ determinants (88 pesticides and 101 non-pesticides (Nutrients, algae and sediment; Microbiological; Hydrocarbon (PAH) and Metals) | As soon as CS water quality data is being collected and shared. | Spot sampling (location review will include CS data). | Currently at downstream sub-catchment level for each surface water catchment operated for water supply by Southern Water. | Potential to deploy higher-tier monitoring equipment and review CS data. | SWS spot monitoring since 2016 and expanded in 2018 on SW catchment networks, frequency dependent on determinant typically monthly. | Ongoing | SWS | Low | High | Continuous to identify any trigger level breach | ARRT and SWS | To be agreed through citizen science workshops (could be shared on data hub) | Arun and Western Rother Catchment | TBC | Arun and Western Rother Catchment | TBD | TBC | TBC | Ongoing | Ongoing, reviewed annually & ad hoc changes made. |  |  | Ongoing | N/a | Integration with citizen science monitoring as collaborative catchment monitoring.
2025 & Beyond CaSTCo
| Investigation | How to engage the wider community (including farmers, community groups, private land owners, and more) in monitoring soil health using lessons learnt from Soil SmARt? | To understand local soil health and to educate local communities on the importance of soil, and how to improve it. We could signpost to other resources and additional help for improving soil. Access to different people for possible habitat enhancements | To create a Soil Guardians Toolkit that can be used to monitor and edcuate about soil health in the local area. | Planning started in year 2, monitoring will start in year 3 | Survey form - soil infiltration, earthworms, pH, VESS, root depth, species richness, bury your undies, soil texture, rhizosheaths | Arun demo area | Learning from Soil SmARt to set up a new soil guardians Toolkit. The surveys will be checked for errors or unusual data points. | This monitoring will give us a baseline understanding of soil health in the area | Every 6 months - spring and Autumn Sampling | WSRT using lessons from Soil SmARt | Low | Med | Continuous | WSRT | Workshops, Reports, Scorecards? Further investigation is required. | Arun and Rother | Cartographer | Arun and Western Rother Catchment | TBD | Report, cartographer |  | Ongoing
| Investigation | Are there correlations or relationships between Soil SmARt/Guardians Soil Health Data and River Guardians/EA Water Quality.River Health Monitoring?
| Surveillance | Mudspotter CS - Identify Source, Pathways and Receptors of sediment over land. Can Mudspotter help us link Soil and Water Health?
| Investigation | How does CS River Guardians River Health Data (Tier 1) compare to Lovibond MD610 & Hach SL1000 (Tier 2) and EA NLS/SWS Lab and Independent Lab Data (Tier 3)
| Investigation | How to effectively utilise River Guardians Data for Positive Change? Utilising River Health Scorecards, Data Dashboards and CS workshops. How can this data push projects, local action and policy change?
| Investigation | Can we identify annual change in waterbody subcatchments River Health? Utilising a score based methodology combing CS data and external sources? |  | Track subcatchment River Health annually using River Guardians Data (Nitrate, Phosphate, TDS< Turbidity) and External data (RHS Habitat Abundance/Diversity Surveys, Pollution Spill Frequency, INNS (CS & INNS Mapper) and Invertibrates (EA Catchment Explorer)
| Project Appraisal | What have Citizen Scientists gained from participating in CaSTCo WSRT River Guardians ? Wellbeing? Knowledge? Awareness? Physical health? Networking/Connections?
| Investigation | Case Study - River Lavant Can we better understand the sources of Nutrients within the Lavant catchment? How can we utilise the WoE Eutrophication tool and push action to further monitor/improve the Lavant.
| Project Appraisal | What have Citizen Scientists gained from participating in CaSTCo WSRT Soil Guardians ? Wellbeing? Knowledge? Awareness? Physical health? Networking/Connections?
| Investigation | Does River Guardian Scorecards/Data Dashboard correlate/support EA RNAGs/Catchment Explorer Status'? Are we finding similar issues in similar locations?
| Future Project Appraisal | Can an annual review of the Collaborative Monitoring Plan enhace collaboration between southern water, WSRT and the EA?
Can 6 monthly catch ups/reviews between the WSRT River Guardians and SWS Clean Rivers & Seas Task Force push positive action/identify hotspots and progress projects with SW Assets?
How can EA & SW best integrate CS WQ Data to push projects/future monitoring etc? e.g. create Streamlined RG Incident Reporting or Trigger Levels for Phosphate/Nutrients recorded for further investigation