## Lark Overview
River Lark Collaborative Monitoring Plan
Item No. | Why |  |  | What | Where | How |  |  | When |  | Who | Feasibility |  |  | Comments
| Type of Monitoring | Objective | What problems are we addressing? | Hypothesis/Objective Statement | Location | Methods | Use | Details | Timing | Duration | Who is going to do this? | Cost | Resourcing/Obstacles | Confidence | Lark catchment partners input to the CMP- Please add date of comment
| What type of monitoring? Investigation/Project appraisal/Surveillance |  |  | What is your monitoring objective/what are you trying to observe? (Your monitoring hypothesis) | Which stream/catchment/locale? | What methods are you going to use? | How will you use the data you collect? | Link to workbook sheet with further project implementation details | What periods over the year and how often? (to indicate variability) | How long? event / date / ongoing | Indicate project lead/owner/SME | Can be in kind | Do we have volunteer capacity, or how do we plan to grow it to achieve this? What are the biggest obstacles? | High/ medium/ low confidence that the monitoring will answer the question in column D | RLCP | Anglian Water | Rivers Trust | Environment Agency | Natural England | CamEO
Lark 1 | Investigation | Where are the data gaps in the Lark catchment | See below rows | Collaborate with partners to review and identify gaps in the evidence base for the Lark to target CS & other monitoring effort as required. To be carried out as needed before proceeding with new citizen science investigations. | Lark and sub-catchments | 2020 EA report on the condition of the Lark and its tributaries could be a good starting point. | To inform next steps of Lark CaSTCo work | [7 empty] | Throughout year 1, ongoing | Agree- 04 Jan 2024 |  | 2020 EA report on the condition of the Lark and its tributaries could be a good starting point.
Lark 2 | Investigation | What is the current physicochemical condition of the Lark’s tributaries? Is there evidence to suggest more attention given to the tributaries could improve the condition of the Lark? | Various - See e.g. EA 2020 River Lark ecological condition assessment | To identify problem reaches/point sources & diffuse pollution to help target remedial measures | Lark Catchment | Mudspotter, Scimap |  |  |  |  | RLCP- Steph Holland |  |  |  | Lark Flagship requirements will need to take priority | Agree with RLCP statement - link to APEM Natural Capital report which identified 4 reaches of the Lark to be the highest priority for investigation? | SL - Need to think about how we can upscale CS WQ monitoring around the Lark catchment. | High, especially in regards to sediment inputs and nutrients/ invertebrates. See above for some baseline data.
Lark 3 | Investigation | Can monitoring of flow regimes and sediment loads of the tributaries enable us to assess nutrient load? | Inconsistent and flashy flow regimes deliver nutrient pulses via high intensity and low-duration flooding | To identify problem reaches/point sources & diffuse pollution to help target remedial measures | Starting in Linnet | Range of methods: - CS WQ monitoring e.g. conductivity, turbidity - Mudspotter surveys; - Outfall Safari; - Flow monitoring | Link with EA to better understand sediment issues & CS monitoring |  |  |  | RLCP- Mariana Sandifer |  | Expect to roll this out on the Linnet sub-catchment subject to attracting land owner interest with the help of Natural England and National Trust. Need to train more volunteers to do the flow survey. |  | Limited to the Linnet in Year 1 |  | SL - Link good flow work so far on Lark with Wensum & UEA to develop CS flow monitoring capability | Sediment loads highest priority. Nutrients and flow slighlty lower priority, but still high priority. Investigate mudspotter and citizen reporting of sediment and nutrient inssues on tributaries.
Lark 4 | Investigaton (aspirational add on) | How do pollution and flow regime impact the invertebrate population? Can the species distribution inform targeted pollution reduction to improve river health? |  | To identify problem reaches/point sources & diffuse pollution to help target remedial measures |  | Riverfly/SMART Rivers | [6 empty] | The aspiration is to build both invertebrate sampling and in parallel build an analysis capability. No resource to fully analyse invertebrate results at present |  | Long-term goal, need to know what's going on with all three of these things. The immediate result is the score. New volunteers with relevant experience needed to progress this |  | SL - Link to line 9 (Abbot's Vale) and potential to monitor for impacts on inverts such as flea treatments arising from dog access to the river | High priority in areas where there isn't existing EA invertebrate monitoring.
Lark 6 | Investigation | How will construction of a new housing development along the Lark impact sediment and nutrient pollution? | Quantifying changes to Lark physicochemical parameters in response to changes driven by development of previously arable/pasture riparian land. Engaging local council to mitigate anticipated decline in water quality (short- or long-term, dependent upon effectivenss of controls by developers). | Conversion of agricultural land into impermeable surfaces will drive increased sedimentation of the Lark and drainage of these areas could open new erosion pathways. | River Lark, Abbots Vale https://w3w.co/cavalier.amuse.dice | Existing EA fisheries survey site at Bridge Farm, Rushbrooke. Water Quality Monitoring. Mudspotter? |  |  | monthly water quality monitoring |  | RLCP |  | Yes- Steph and Graham are going out monthly already. |  | High- ongoing monitoring, long-term project /need to get more volunteers |  | SL - Link to line 7. Could also consider Riverfly/Riverfly+ monitoring to assess pre-and post impacts on inverts by new public access and dogs entering the river (flea treatment) | Medium- Results and any pollution reports would be of interest to the EA.
Lark 7 | Investigation Data management system (see also Demo+ deliverable 5.16-3 (Scope change request TBC; develop into CMP with AW/RLCP/EA & partners) | Develop an integrated data management platform that follows FAIR (Findability, Accessibility, Interoperability, and Reusability) principles to optimise the impact of CS efforts and ensure results are understood and acceptable to regulatory scientists. |  | Improve storage, management and availibility of data & evidence in a standardised, accepted way to inform Lark (& wider CamEO) catchment management | [6 empty] | Demo+ |  | Yes- Noma can support visualisation development in an Esri platform. | High | AW deliverable is fundamental for RLCP citizen science progress towards any integrated data | High- key Demo+ deliverable | SL- High priority; link with AW Demo+ and Wensum/WCP initiatives on this theme. | High - Would be extremely useful now and essential that we have this before the end of the CaSTCo project so EA can access citizen science data without having to go through CS coordinator.
Lark 8 | Investigation | Compile and simplify WFD data interpretations to facilitate increased public understanding of river health and key barriers to improvement. | [10 empty] | YES |  | High, action planned with JF |  |  | Medium priority, improved communication with stakeholders is important. Happy to support.
Lark 9 | Investigation | How accurate is the data collected by citizen scientists using various types of equipment? How will the EA and other stakeholders use this data? |  | To test our citizen science sample results against certified lab analysis and EA samples and review & refine CS equipment & methods accordingly; feed results into CaSTCo e.g. Work Package 3: Methods Audit - To work with catchment partners including the EA, NE and AW to ensure CS input & data becomes an accpeted part of the decision making process |  | Case study interventions based on CS data |  |  |  |  | AW Demonstrator monitoring - River Ecology/Link to Demo+ |  | YES |  | AW deliverable is customised to provide answers for the Lark citizen science work | High- part of CMP and CaSTCo as a whole to evaluate citizen science methods | SL - Link with Wensum CS to share results and target calibration needed on the Lark - e.g. high phosphate | High priority, how the EA use citizen science data will be determined by its accuracy.
Lark 10 | Investigation | Is there appetite from local landowners in the Lark catchment to carry out citizen science on their land so they can understand their local impact on water quality? If there is landowner appetite to get involved, how best can the Anglian Demo group in the Lark work with and support landowners in the Lark catchment to carry out citizen science? | Historic lack of engagement with farmers and many other major riparian landowners impedes collaboration in the catchment. Many landowners are hesitant to formally participate in mitigation or conservation schemes due to the strings attached. The degree to which conservation measures are informally implemented on a voluntary basis is unknown. |  | Linnet | Info leaflet to farmers/landowners from RLCP/CSF |  |  |  |  | NE-Michelle Gault |  | YES-link to row 6 |  | RLCP/natural England Linnet farmer initiative underway-October meeting Medium- Engagement with Lark Water Mgmt Forum (group of farmers, other abstractors) NT partnership needs to be documented, as a close relationship. | Interested in this - but dont have dedicated AW Catchment Advisor in this area |  | JL Medium-high priority - would be keen on landowner action to monitor/tackle sediment and nutrient inputs and restore natural function of the river. Would be interested to know if RLCP identify enthusiastic landowners not know to us . Rob Clapham plans Lark-wide initiative in November.
Lark 11 | Training Lark CMP training needs: Capture training and resource needs in CMP | -SMART rivers; RiverFly - New CS volunteers; - Flow monitoring; - Mudspotter; - Outfall Safari - GIS/data management - Water quality monitoring; | To effectively achieve other objectives, volunteers need to be trained to implement. | Train up 10 new volunteers per year | [6 empty] | RLCP- Steph to track training | £1K per year training costs £250 equipment (nets, trays, waders etc) | YES |  | By end of year one. Highest priority is increasing engagement of new volunteers. | Supported already via funding for EA's outfall safari train the trainer event, could link into Riverfly training agreement with Ian Hawkins if there was citizen science interest. | SL - Consider ways to help scale up CS on the Lark | Riverfly and pollution/ sediment input (maybe using mudspotter and poss also outfall safari) monitoring are our highest priorities. Other aspects of chemistry and flow and recruiting more volunteers are high priority. SMART rivers medium priority. |  | Year 1 & Year 2
Lark 12 | Investigation | Can citizen science monitoring demonstrate or help to demonstrate the benefits of habitat enhancement projects. Citizen science could potentially also help with fluvial audit identifying where sediments sources and stores are in the catchment. | TBD- Depends on the Flagship sites chosen | Invertebrate and possibly also chemistry/turbidity/fish/plant data might be able to demonstrate the benefits of habitat enhancement schemes | Downstream of Lackford Link to project planning/feasibilty scoping for Lark Flagship | Suggest ecology monitoring Riverfly plus/Riverfly. Maybe also plants/fish/chemistry/ flow/turbidity. | Report (ideally citizen scientists supported by EA or vice-versa). |  | Ideally to start at least 1 year before any enhancement works. | 1-2 years before any enhancement work, during the work and then ideally years 1, 2, 3 5 and 10 after. | Lark Flagship (RLCP+AW) |  | No scoping has been carried out on the frequency/variety of monitoring needed to be effective |  | EA feasbility Flagship project downstream of Lackford about to go live. Any citizen science support woud be a first priority for RLCP |  | SL - Link with Lark Flagship if CS can help deliver pre-project monitoring of potential habitat schemes | Medium-high keen to investigate how how well any enhancement project in this stretch works. Important to do some pre-works monitoring before project begins.
Lark 13 | Long-term investigation | What are the factors contributing to a recurrence of poor EA invertebrate scores/failures and eutrophication on the Lark between Sicklesmere, Hengrave and Lackford? |  |  | Between Sicklesmere and Lackford | Various TBC, including desk assessment of AW discharge network map, public engagement in urban Bury, Outfall Safari during dry weather |  |  | Over time- past 23/24 due to scope of questions to be addressed. Evidence needs to be built up. |  | can EA contract to undertake this work |  | Lack of knowledgeable volunteers to conduct analysis long-term |  |  |  | High priority - need to develop a strategic framework within the CMP to address what could be a number of contributory factors | JF (2/6/23) Problems likely linked to eutrophication & excess algae growth. Larger trigger level breahces previously occurred in 2018/19.
Lark 14 | Investigation Baseline AW Demo + deliverable 5.14-1 (Scope change request TBC; develop into CMP with AW/WCP) | Monitoring upstream & downstream of descriptive STWs in catchment | Absence of robust information about tributary status and how descriptive works may affect that; citizen scientists' results have not been validated using lab results in the Lark catchment. | Collaborate with AW specialist contractor to co-design robust monitoring of selected descriptive works in the Lark catchment, ensuring citizen science engagement | [8 empty] | Will this be limited to descriptive works? Could be used to deliver the CS validation, another objective. Need to have a timeline of when this will happen and if monitoring would be in parallel. |  | Detailed context with AW contractor requested to allow input to specification | Demo+ scope change request approved 6 June23
Lark 15 | Investigation Lark catchment recreational hotspots (Aspirational) | Do sewage effluent inputs to the Lark catchment contribute to increased risks for river users (E. coli)? | Mitigating health risks to river users. | To collaborate with others to establish low cost E. coli monitoring at selected sites | Key recreation sites in the Lark catchment | Explore low cost CS options e.g Aquagenx Compartment-Based Tests (CBT) |  |  | Revisit in Year 2 to consider implementation Year 3 |  |  | Compartment Based Tests (Aquagenx) £475 per 50 tests (£9.50/test) | Could collaboration with Little Ouse volunteers help with training and monitoring? |  | Lack of resource for full study.Propose that AW Demonstrator "descriptive sites" includes this.-see above
Note on C14: ====== ID#AAAA4RQBmIs tc={53D70368-BFCF-448A-AD19-CAB62B315BF9} (2023-08-16 12:27:40) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the wrong place for these details- should be put in the HOW section. What is our objective of these?