## Teme_V2
Version 2 Review | Why | Why | Use | What | Priority | How | Where | QA | Data | When | Who | Cost | Confidence | When to stop | Evaluation | Visualisation | Location | Storage | Archive data? | Format | Where stored? | How long?
Steering Group members to add notes on whether questions should be kept for 2024, any changes or updates required | What type of monitoring question? 1) Current state (health, issues) 2) Investigation (determine causes, impacts, target interventions) 3) Prediction 4) Impact of intervention (project appraisal) | Write the aim of the monitoring in the form of a question | How will you use the data you collect? | What is your monitoring objective/what are you trying to observe? (Your monitoring hypothesis) | Year 1, Year 2 or beyond | What methods are you going to use? | Location | What QA procedures will you use? | Add information on the baseline data you have collected (type, frequency, method used) | What periods over the year and how often? (to indicate variability) | Who is going to do this? | (Can be in kind) | High/ medium/ low confidence that the monitoring will answer the question in column B | When to stop monitoring? Date (inc macro to highlight data which should no longer be collected) | Who who will collate and evaluate the monitoring results? | How will you present and share the monitoring results? | Name of water body | How will you store the data | Archive data? Yes/No | Spreadsheet/WIMS/report/other | Where archived? FWW/FBA/WIMS/local | event / date / ongoing
Q for SRT: Funding for lab monitoring? How much money can be spent on CS bacti kits? This is going to influence which method can be used (LA). SRT monitoring budget has been mostly spent now, so any additioanl funding for bacti kits / lab monitroing will require additional fundraising and/or funds from the central CaSTCo pot (AF). | Overarching | What is the extent of bacterial pollution within the Teme, wrt bathing water standards? | CH - if specific sources are identified in Wales this can be flagged to appropriate regulation officers at NRW for investigation / follow up | Monitoring for bacteria hotspots and potential sources. | Y1 monitoring trials complete. Jan-Feb 2024: steering group to assess pros and cons of different bacti methods and decide which to start or continue in 2024. | Initial trail combining and comparing lab analysis and AquagenX kits. Also going to trial CEH eDNA kits to look at source apportionment. Future methods may include MolEndoTech BacterisK+ device, sediment analysis and tampon test. | Existing bathing areas Lower to mid-Teme including Ashford Carbonel, Leintwardine, Ludlow, Tenbury. Canoeing, paddle board areas. UPDATE: Looking at the wider Teme catchment and gaps in current monitoring. | All volunteers trained in following aseptic sampling protocol. Samples sent to lab for comparison. | No broad baseline data But SvTW have collected data 2022 Annual / ongoing NRW water quality sampling results. WFD assessment info for Teme waterbodies. Number and location of permitted STW and agri units. Record of any incidents reported. | All year round | CS volunteers with support from volunteer coordinator. Analysis likely done by 3rd party.
Have we now answered this Q? (AF) | Investigation | Where are the gaps in our knowledge and exisiting monitoring? | To inform next steps of Teme CaSTCo work | To establish what is currently being monitoring and where. | Completed for Year 1 (2023). Year 2(2024): Work ongoing to update baseline maps, to inform monitoring locations for 2024, to fill gaps and identify sites that can be used for data validation. | Map excercise of existing monitoring points. Get source aportionment data for phosphate from EA data. |  |  | EA, NRW, STW, volunteer groups, Angling Trust records | From predermined set date but to include historic data collection points. Renew at end of project period. | Project partners |  |  |  |  | GIS Map? |  | CaBA Data Explorer
MURAL has been set up to assess this. I think it would also be worth having a conversation with Kat (LA). | Initial investigation | What methods of bacteria monitoring are available and suitable for citizen science. | To steer the direction of future bacteria sampling across the catchment. | To trial different methods of bacteria sampling against lab analysis samples to determine the level of accuracy | Y1 monitoring trials complete. Jan-Feb 2024: steering group to assess pros and cons of different bacti methods and decide which to start or continue in 2024. | Waterblitz trials to compare various methods. | Various sites throughout the Teme catchment. | Lab analysis for comparison. |  | Initial trial to invovle weekly sampling from end Sep -end year 23. | CS volunteers with support from volunteer coordinator, Tim Harris (TH Environmental) & Simon Browning (RT).
Still awaiting results from eDNA filters (KA) | Initial investigation | Is it possible to accurately collect data on source apportionment of bacteria using methods suitable for citizen scientists? | To steer the direction of further source apportionment data collection across the catchment with volunteers. | To see if it is possible for citizen scentists to collect data that allows us to accurately identify bacteria sources in a rural catchment using eDNA kits. | Awaiting results from Y1 trials. May be options for reviewing land use, stocking density etc to contirbute to this analysis. Would like to do a second trial in Spring/Summer Y2. | 25 no. CEH eDNA kits | Initially across the 7 trial sample sites listed above. | All volunteers trained in following aseptic sampling protocol and have followed video guidance provided by CEH on using the eDNA kits. |  | Initial trial
Suggested focus for Y2 trials, so long as we can collect bacti data in some form? (AF) Will soon be ordering DIY turbidity tubes (KA) | Future investigation | Can proxi measures be used as accurate indicators of high bacteria levels? |  | Test the use of proxi measures as indicators of bacteria levels. | 2024 monitoring to continue and extend chemical testing, add turbidity, electro-conductivity, and explore other possible proxi-measures too. | Turbidity testing, ammonia, phosphate, nitrate, electrical conductivity | Location may depend on no. kits available through Wateraware project. Potentially trial in same areas as bacteria sampling trial has been carried out as will have knowledge of baseline bacteria levels to compare against. | TBC | Will have some baseline data on bacteria levels from previous CS trial. | TBC (will depend on Wateraware project) | CS with support volunteer coordinator.
Will this be simple to investigate if we are collecting temp and bacti data? (AF) | Future investigation (aspirational add on) | Does river temperature impact upon the presence and abundance of harmful bacteria (FIO)? |  | River temperarture and presence of FIO | Temperature recording included in Y1 trials and continued in Y2. | Thermometer & some form of FIO analysis | All sampling sites |  |  |  | CS volunteers with support from volunteer coordinator. Analysis likely done by 3rd party.
Suggested focus for Y2 trials (AF). | Investigation | Are there particular phosphate hotspots within the Teme catchment? | CH - if specific sources or hot spot areas are identified in Wales this can be flagged to appropriate regulation officers at NRW for investigation / follow up | Which tributary contributes the highest P levels to the river Teme | trialled in y2, to be continued and expanded in y2. | Spot sampling using Hanna checkers Spatial mapping of land use/farm location Catchment cattle count | All tributaries - need to know where existing monitoring carried out to help with data validation |  | WIMS phosphate Catchment walk over / survey results Annual / ongoing NRW water quality sampling results. WFD assessment info for Teme waterbodies. Number and location of permitted STW and agri units. Record of any incidents reported. | All year round - 2 weekly/monthly? | CS volunteers with support from volunteer coordinator. |  |  |  |  | Identification of specific waterbodies / tribs Catchment map similar to Westcountry CSI map
Would be good to get outfall safari going on the Teme (LA). Agreed! (AF) | Investigation | Where are the misconnections that are polluting the river Teme and its tributaries? (MF Does this also need to include livestock entering rivers) | CH - if areas requiring investment in riparian fencing (to prevent livestock access) are identified, NRW and SRT Inshore Fisheries Habitat Restoration Programme could consider in prioritisation of work in future funding years | To locate outfalls across the catchment and assess them for evidence of pollution. | LM - Links with above. due to recent Paul Whitehouse press coverage possibly high riority for citizen scientists | Outfall safari, tampon method | Initially urban areas |  |  | Summer months due to misconnection signal being stronger when there is no runoff/CSO overflow | [5 empty] | GIS layer recording walkover findings?
Very dependant on money available for lab analysis. Potentially one to drop if too expensive? (LA) | Investigation | What levels of antibacterial microbial resistance are present within water and sediment samples? |  | Antibacterial microbial resistance | LP - vote Yr 2/3 | Lab analysis | Same as above
SRT e-fishing surveys for salmon phd will pick up fish species, may be possible to tie-in to some bathing sites (AF). | Investigation | Is there overlap in bathing/ recreation areas and the presence of sensitive species i.e. freshwater pearl mussel, salmon, trout, white clawed crayfish and shad? | CH - if there is overlap in areas of recreation and protected species range in Wales, NRW Mid Wales People & Places Team could look to produce comms to inform responsible water use | To establish the presence and the range extent of species within the Teme | LP - vote Yr2/3 LM - this will come up in the mapping exercise aswell but real caution required re FPM - we should not be advrtising where the mussels are | Surveying of bathing/recreational areas eDNA sampling (LP - Nature Metrics?) |  |  | SAC data on White Clawed crayfish, Ashford Mill fish counter, NRW annual fish survey findings and crayfish records | Recreational areas survey - summer time eDNA sample collection - May? (based on shad) | CS volunteers surveying recreational areas and collecting samples.
Is this data being collected by volunteers looking to get bathing water status? LA | Investigation | How do people use the River Teme and what benefits do they gain from doing so? | CH - if angling is identified as a key use of the Teme in Wales, NRW's Sustainable Fisheries Funding (reinvestment of rod licence duties) could be used to support angling infrastructure projects | Social benefits of blue/green infrastructure | LP - vote Yr 2/3 OD - This could be a good way of introducing CaSTCo to the wider populaiton and local communities, in which case it could possibly be done sooner? | Survey of numbers and types of river users Open source/social media data scraping for rivrer health impact of river users |  |  | SvTW have collected some data on bathing areas | [6 empty] | Infographic?
It would be great to get some morphological surveys going but may be a step too far for time-frame? (LA) | Investigation | What impact do high amentity areas have on the river environment? | CH - if there is overlap in areas of recreation and protected species range in Wales, NRW Mid Wales People & Places Team could look to produce comms to inform responsible water use | To assess the impact of high amentify areas. | LP - vote year 1 OD - agree, as above this is a good way of introducing CaSTCo to the wider populaiton and local communities. Esp. the litter surveys. | Add simple checklist to Survey123 e.g. can you see: litter, bankside erosion, anti-social behaviour etc. |  |  |  | Summer months - highest number of visitors | CS volunteers
Remove question? | Investigation | Does the Teme make people sick? |  | Number of sickness reports | OD - longer term study? Or is this information already collected? | Environmental health surveying and reviewing sickness reports |  |  | Public health data, Surfers Against Sewgae data
This sort of question can be added to survey that volunteers fill out when carrying out spot samples. also links to habitat/morphology surveys (if that goes ahead) (LA). | Investigation | How do does flow rate link to water quality and bacteria levels in the Teme? | CH - this info could feed into NRW's Mid Wales Flood Risk Management Plan. Identified communities can be supported by NRW in Community Flood Planning. If sites ideal for NFM / flood plain reconnection are identified in Wales, these can be flagged to NRW's national River Restoration Programme Team (who run large scale projects of this kind). A map of areas affected by drought could be used by NRW's North Wales Drought Group for targetting watercourse monitoring / potential fish rescues during summer months. | How effective are NFM interventions and which areas dry up | CH - like this and would be v interesting from NRW's perspective, but is slightly removed from the other WQ-related Qs? OD - drought most relevant. Amount of water influences dilution and so water quality. Also impacts quantity of bathing water available and appearance of bathing water (algae). Interesting and useful information to collect. Vote - Yr 1 LM - fixed point photography would be relativelty simple | Flow rate question on Survey123 |  |  | Teme abstraction licencing strategy Wales Flood Risk Map viewer: https://maps.cyfoethnaturiolcymru.gov.uk/Html5Viewer/Index.html?configBase=https://maps.cyfoethnaturiolcymru.gov.uk/Geocortex/Essentials/REST/sites/Flood_Risk/viewers/Flood_Risk/virtualdirectory/Resources/Config/Default&layerTheme=0
This sort of question can be added to survey that volunteers fill out when carrying out spot samples. also links to habitat/morphology surveys (if that goes ahead) (LA). | OD - Value in making a link with biodiversity? Perhaps not obvious bathing water priority, could be useful strand of data/evidence. | Wildife as indicator of water quality and habitat. Presence enhances visitor experience. Engages citizen scientists. Create space on future data portal or app for/linking to this kind of information? |  | River Naturalness surveys, uses existing app. Teme headwaters key target site for this work. Possibility of eDNA reference fresh water pearl mussel and fish (shad etc). Longer term study of data from bird surveys such as dipper and grey wagtail. Clun Monitoring group member already undertakes surveys and charts/publishes results.
[8 empty] | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | ---